## Slide 1: CATSystem Cancer Tracking System
Project Development Plan
Kevin Oyowe
May 31st, 2019 UPDATED: July 29th, 2019

## Slide 2: Methodology
Evolutionary Prototyping model

## Slide 3: Methodology
In the Evolutionary Prototyping Software Development model, an actual functional prototype with minimal functionality is built in the beginning. The prototype developed forms the heart of the future prototypes on top of which the entire system is built.
This method was chosen as the ideal model for the CATSystem project since a skeleton prototype of the system already exists, a pilot site for the CATSystem project has been identified, the end-users are available, and there is sufficient data to test with.

## Slide 4: Development Plan
Project Development Plan

## Slide 5: June 2019 (1st Prototype)
2019
1 day
1 day
19 days
1 day
5 days
5 days
5 days
3 days
3 days
1 day
1 day
First CC Screening Form (Release of Initial system prototype – Non-Hosted)
Logical Database Design (Paper work)
Physical Database Design (Computer work)
2019
Today
Week 1
2
3
4
5
Create Project Plan
5/31/2019
Holiday - Madaraka Day (KE)
6/1/2019
6/3/2019 - 6/21/2019
Project Development Phase I
Kick-off communication
6/3/2019
6/3/2019 - 6/7/2019
Database Analysis &
Design - Step 1
6/10/2019 - 6/14/2019
Database Analysis &
Design - Step 2
6/17/2019 - 6/21/2019
Application Development
Progress Report
6/24/2019 - 6/26/2019
6/25/2019 - 6/27/2019
Feature Tests
Executive Review
6/27/2019
Proposed Changes & New Features Report
6/28/2019

## Slide 6: July 2019
2019
Today
26 days
1 day
5 days
1 day
5 days
5 days
5 days
3 days
3 days
1 day
1 day
Choice of web hosting and location, domain name purchase, SMS plan, & Subscription budgets.
2019
Week 1
2
3
4
5
7/1/2019 - 7/26/2019
Project Development Phase II
Kick-off communication
7/1/2019
7/1/2019 - 7/5/2019
Hosting & Domain
Holiday - Independence Day (US)
7/4/2019
7/8/2019 - 7/12/2019
Travel plans
Training &
Orientation Wk1
7/15/2019 - 7/19/2019
Training &
Orientation Wk2
7/22/2019 - 7/26/2019
Progress Report
7/29/2019 - 7/31/2019
7/30/2019 - 8/1/2019
Feature Tests
Executive Review
8/1/2019
Proposed Changes & New Features Report from P-I & P-II
8/2/2019
Travel & arrival plans to Kansas City
Arrival and orientation
Orientation & mentorship on HITSystem technology/software stack
Hosting & Domain follow-up and support

## Slide 7: August 2019 (2nd Prototype)
2019
Today
19 days
1 day
5 days
5 days
5 days
3 days
3 days
2 days
1 day
2019
Week 1
2
3
4
8/5/2019 - 8/23/2019
Project Development Phase III
Kick-off communication
8/5/2019
8/5/2019 - 8/9/2019
Improvements & Bug Fixes
8/12/2019 - 8/16/2019
Feature developments
8/19/2019 - 8/23/2019
Feature developments
8/26/2019 - 8/28/2019
Progress Report
8/27/2019 - 8/29/2019
Feature Tests
Executive Review
8/29/2019 - 8/30/2019
Proposed Changes & New Features Report
8/30/2019
Work on proposed changes and bug fixes
Develop proposed features.
Introduction of SMS services
Develop new & proposed features (Release of 2nd system prototype - Hosted)

## Slide 8: September 2019
2019
Today
19 days
1 day
5 days
5 days
5 days
3 days
3 days
2 days
1 day
2019
Week 1
2
3
4
9/2/2019 - 9/20/2019
Project Development Phase IV
Kick-off communication
9/2/2019
9/2/2019 - 9/6/2019
Improvements & Bug fixes
9/9/2019 - 9/13/2019
Features Development
9/16/2019 - 9/20/2019
Features Development
9/23/2019 - 9/25/2019
Progress Report
9/24/2019 - 9/26/2019
Feature Tests
Executive Review
9/26/2019 - 9/27/2019
Proposed Changes & New Features Report
9/27/2019
Work on proposed changes and bug fixes
Develop new & proposed features
Reporting & Dashboard design and development

## Slide 9: October 2019 (Final System)
2019
Today
19 days
1 day
5 days
1 day
5 days
5 days
1 day
1 day
3 days
3 days
2 days
1 day
2019
Week 1
2
3
4
10/7/2019 - 10/25/2019
Project Development Phase V
Kick-off communication
10/7/2019
10/7/2019 - 10/11/2019
Improvements & Bug Fixes
Hoilday - Moi Day (KE)
10/10/2019
10/14/2019 - 10/18/2019
Features Development
10/21/2019 - 10/25/2019
Features Development
Holiday - Mashujaa Day (KE)
10/21/2019
Holiday - Diwali (KE)
10/27/2019
10/28/2019 - 10/30/2019
Progress Report
10/29/2019 - 10/31/2019
Feature Tests
Executive Review
10/31/2019 - 11/1/2019
Proposed Improvements Report
11/1/2019
Work on proposed changes and bug fixes
Develop new & proposed features
(Release of 3rd system prototype – Final System)

## Slide 10: Testing plan
System Testing Plan

## Slide 11: System testing
The project development plan has a provision for feature tests at the end of each iteration, however, the final product will be tested using the Manual Testing method.
Manual Testing is the process of using the functions and features of an application as an end-user would in order to verify that the software is working as required.
The process will involve first writing down the system requirements/functionalities to be tested, then developing detailed test cases for each requirement before the actual tests are conducted and a Test Report compiled.

## Slide 12: Testing
2019
Today
12 days
1 day
2 days
5 days
2 days
1 day
5 days
1 day
5 days
3 days
2 days
1 day
Test & Log bug reports where applicable.
2019
Week 1
2
3
12/2/2019 - 12/13/2019
System Testing
Kick-off communication
12/2/2019
Write Test Requirements
12/2/2019 - 12/3/2019
12/2/2019 - 12/6/2019
Prepare the Test Environment
Develop
Test Cases
12/4/2019 - 12/5/2019
Review
Test Plan
12/6/2019
12/9/2019 - 12/13/2019
Conduct The Tests
Holiday - Jamhuri Day (KE)
12/12/2019
12/9/2019 - 12/13/2019
Log Errors and Bugs
Report on
Test Results
12/16/2019 - 12/18/2019
Executive Review
12/19/2019 - 12/20/2019
Final Decision
12/20/2019

## Slide 13: Green Light
Proceed with System Implementation